## Sheet1
the gantt chart tasks are based on deliverables that are based on the objectives. | week 1 | week 2 | week 3 | week 4 | week 5 | week 6 | week 7 | week 8 | week 9 | week 10 | week 11 | chrismas week 1 | chrismas week 2 | chrismas week 3 | week 12 | week 13 | week 14 | week 15 | week 1 sem2 | week 2 sem2 | week 3 sem2 | week 4 sem2 | week 5 sem2 | week 6 sem2 | week 7 sem2 | week 8 sem2 | easter week 1 | easter week 2 | easter week 3 | easter week 4
research done on similar solutions (1.1) | bar: week 2 to week 5
learning python and its libaries such as numpy,scipy, scikit-image, opencv-python (2.1, 2.2) | bar: week 3 to week 9
Look at the types of plastics that are causing problems in the ocean such has bottles, fishing nets bouys (1.2) | bar: week 2 to week 8
research done on potential embedded hardware that can be used for this project (3.1) | bar: week 3 to week 6
choosing the camera that is compatible with board chosen. (3.2) | bar: week 6
finding out about quality of the camera is the most impactful on the object detection algorithm and find the best height for the board to be up in the air with the camera . (3.3 ,4.1) | bar: week 6 to week 9
do resarch on different algorithms that can be used to impelement a object detection programme for this project (2.3) | bar: week 5 to week 7
choose the best algorithm base on your own experimentations that can be used for your this project to detect harmful plastics in the ocean that is complatible with your board. (5.1)
train and test the algorithm that is used for object detection (7.1, 5.2)
implemenation of the trained algorithm into the board (6.2)
implement version control in case you need come back to older version of programme if current one is beyond slavagable (7.3)
establish a test plan and constantly test the capability of the current system. (7.2)
write the final report | bar: week 1 to week 2
other subjects.